## Overview
SOURCE VISION — DECISION LOG
Live register of every locked and open decision · NexusLink internal
Owner | Vijay Dabhi · vijay@nexuslinkservices.com · +91-9909265786
Prepared by | NexusLink Services India Pvt. Ltd.
Client | Blue Virtue
Project | Source Vision (Acquire-ready demo + future platform)
Version | v1.0 · 1 September 2026
Purpose | Track every material decision — Locked and Open — plus the Development & IP Register. Update in place, do NOT create new versions.
SHEETS IN THIS WORKBOOK
Sheet | Purpose
Locked Decisions | Every decision that is signed off. 25 rows pre-populated. Add new rows as decisions lock.
Open Decisions | Every decision still pending or with the client. 16 rows pre-populated. Move to Locked when resolved.
IP Register | Development & IP Register. Blue Virtue's day-1 requirement. 6 starter rows. Add every new component.
Change Log | Every material change to this workbook. Who changed what, when.
HOW TO USE THIS WORKBOOK
1. When a decision LOCKS: add a row to 'Locked Decisions' with today's date, source, and rationale. Move it from 'Open Decisions' if it was there.
2. When a NEW OPEN DECISION arises: add to 'Open Decisions' with priority and owner.
3. When a NEW COMPONENT is built or added: log in 'IP Register' — this is not optional, Blue Virtue require it from day 1.
4. Update MEMO in 'Change Log' for every session where you modified the workbook.
5. Column widths: do not narrow them. Rationale text needs the room.
6. NEVER delete a row from Locked Decisions — decisions get superseded, not deleted. Add a new row that supersedes the old.
7. Filter and sort freely. Save often. This workbook is version-controlled by content, not by filename.

## Locked Decisions
ID | Date | Area | Decision | Rationale / Source | Impact / Notes
L1 | 2026-08-11 | Build approach | Two-phase build: Phase 1 static HTML, Phase 2 Laravel+Vue | Understanding doc v1. Vijay explicit: 'make it html only for now'. | Structural decision. Guides all Phase 1 tech.
L2 | 2026-08-11 | Data | Dummy data only in Phase 1. No real data of any kind. | Understanding doc + brief. | Applies to every screen. No forms submit.
L3 | 2026-08-11 | Language | English throughout Phase 1 | Understanding doc. | Newsletter Overview may show Dutch GRS screenshots as heritage.
L4 | 2026-08-11 | Currency | EUR (€) throughout | Client brief + all designs. | No USD/GBP/INR anywhere.
L5 | 2026-08-11 | Brand system | Brand system locked by Blue Virtue Development Handover | Colours #192A4B / #001FFA / #FD5104. Space Grotesk. Logo assets. | See source-vision-design skill / Project Bible §19–22.
L6 | 2026-08-11 | Reporting | Campaign Reporting Dashboard built natively — Meneer Online iframe rejected | Iframe is Dutch UI, live analytics, off-brand, breaks dummy-data rule. | Custom-build for Phase 1. Phase 2 reporting to reassess (see O9).
L7 | 2026-08-11 | Phase 2 stack | Laravel 11 + Vue 3 + Inertia + MySQL 8 + Vite + Tailwind + spatie/laravel-permission | Understanding doc. Blue Virtue accepted 31 Aug subject to portability/documentation. | Tailwind config shared with Phase 1 to migrate tokens cleanly.
L8 | 2026-08-11 | Architecture | Single-DB multi-tenancy with CSS-custom-property re-theming | Understanding doc. | Enables per-tenant subdomains + branded themes.
L9 | 2026-08-12 | Services | eMagazine WITHDRAWN — build nowhere | Every eMagazine reference in client brief struck through. | Do NOT show in dashboard, service selection, packages or reporting.
L10 | 2026-08-12 | Team | Jelle removed from delivery team | Jelle's capacity block struck through in the brief. | Rebaseline capacity with this in mind (see Bible §29).
L11 | 2026-08-12 | Copy | Homepage hero stat = '~100,000 employees using Source Vision platforms worldwide' (not 'users') | Fact-check against client brief. | Exact wording — no reinterpretation.
L12 | 2026-08-12 | Homepage | Trusted-by row uses placeholder logos, not real third-party (Cisco / Uber etc.) | Client brief uses real logos without permission — replace. | Use generics: 'Retail Co', 'North Group', 'Studio 41'.
L13 | 2026-08-31 | Wave 1 storyline | Wave 1 must tell full 10-minute commercial story: Login → Customer → Services/Plans → Request → Campaign/Lead Gen → Results → Admin → White-label | Blue Virtue Alignment Note. | Shapes Wave 1 order and content.
L14 | 2026-08-31 | Wave 1 scope | Campaign Request Flow, Scratch Game / Lead Gen, Campaign Reporting = Wave 1 (demo depth) | Blue Virtue Alignment Note — pulled forward from Wave 2. | Adds ~20–35h to Wave 1. Re-baseline capacity Options A/B/C.
L15 | 2026-08-31 | Wave 1 scope | Public Homepage deprioritised in Wave 1 — trim first if capacity tight | Blue Virtue Alignment Note. | Homepage remains but is not a Wave 1 protected screen.
L16 | 2026-08-31 | Naming | 'Developer view' renamed 'Platform Owner / Settings' — 3 portals now Customer, Admin, Platform Settings | Blue Virtue Alignment Note. | Update in ALL docs, mockups and menu labels.
L17 | 2026-08-31 | Pricing framing | Plan / package pricing shown = example monetisation model, configurable by owner | Blue Virtue Alignment Note. | Add small label wherever pricing appears in the demo.
L18 | 2026-08-31 | Phase 2 wording | GRS Data Migration renamed 'Generic Data Import & Migration Tools' — no GRS data assumed | Blue Virtue Alignment Note. | Update Phase 2 Module Overview v2.
L19 | 2026-08-31 | Phase 2 framing | Phase 2 = 'Proposed Full Platform / Future Product Architecture' — framework only, not committed build | Blue Virtue Alignment Note. | No Phase 2 effort/cost estimates in client-facing docs until framework signed.
L20 | 2026-08-31 | Phase 2 modules | AI Campaign Assistant + Print Portal = ROADMAP only in Phase 2 | Blue Virtue Alignment Note. | Move out of core Phase 2 module list.
L21 | 2026-08-31 | Phase 2 architecture | Integrations Layer split into: core / optional third-party / API framework | Blue Virtue Alignment Note. | Not one implementation effort — advertising / analytics / CRM / print / payments are separate.
L22 | 2026-08-31 | Content Library | Content Library allowed as simple asset organisation; legacy GRS folder module EXCLUDED | Blue Virtue Alignment Note. | Reword description so it does not read like a GRS carry-over.
L23 | 2026-08-31 | Phase 2 priority | Multi-tenancy / White-label = strategic priority of Phase 2 | Blue Virtue Alignment Note. | Shared codebase, tenant separation, custom domains, branding, roles, data separation.
L24 | 2026-08-31 | Infrastructure | Phase 1 hosting = Blue Virtue VPS. Demo domain = source-vision.com on Cloudflare. MVP infra only. | Blue Virtue Alignment Note. | Not a production hosting commitment.
L25 | 2026-08-31 | IP / traceability | Development & IP Register maintained from day 1 of Source Vision implementation | Blue Virtue Alignment Note. | See 'IP Register' sheet. Update on every new component.

## Open Decisions
ID | Date raised | Area | Question / decision | Owner (who answers) | Priority | Status | Notes
O1 | 2026-08-11 | Pricing | Franchise Plan pricing: €999 (Plans page) vs €1,049 (Upgrade page) — reconcile | Blue Virtue | High | Awaiting client | Recommend €999 (matches primary Plans page).
O2 | 2026-08-11 | Pricing | Custom Campaign Support: €299 standalone vs €99 as add-on — reconcile | Blue Virtue | High | Awaiting client | Two products, or same product mispriced?
O3 | 2026-08-11 | Naming | Admin plan vocabulary (Basic / Standard / Pro) does not match 5 customer plan names | Blue Virtue | Medium | Awaiting client | Use the 5 plan names everywhere, or add a mapping.
O4 | 2026-08-11 | Terminology | Client brief calls 5 tiers 'Packages'; designs call them 'Plans'. Which stays? | Blue Virtue | High | Awaiting client | Recommend adopting designs' terminology (Plans = 5 bundles, Packages = 8 single-service cards).
O5 | 2026-08-11 | Typography | Buttons: Space Grotesk (all mockups) vs Inter (handover text) | Blue Virtue | High | Awaiting client | Default assumption: Space Grotesk everywhere including buttons.
O6 | 2026-08-11 | Design tokens | Exact light-grey tokens, border colour, corner radius, spacing scale — pull from designs or ask | Blue Virtue / PM | Medium | In progress | Some can be derived from designs; escalate only for ambiguous cases.
O7 | 2026-08-11 | Design tokens | Navy gradient exact stops (Gradient_Image.jpg reference) | Blue Virtue | Low | In progress | Can be measured from reference image.
O8 | 2026-08-11 | Design system | Icon library choice (Heroicons / Lucide / Blue Virtue's set) | Blue Virtue / PM | Medium | Awaiting decision | Confirm in Week 1 so developer starts consistent.
O9 | 2026-08-31 | Reporting tech | Blue Virtue dashboard technology — reference / demo / documentation for reporting reuse assessment | Blue Virtue | High | Awaiting client | Needed BEFORE Phase 2 reporting quote. Could shrink Phase 2 effort materially.
O10 | 2026-08-31 | Resourcing | Capacity option A/B/C for the September build | Blue Virtue + Vijay | CRITICAL | Awaiting decision | Must be closed before build kick-off.
O11 | 2026-08-31 | Legal | One-page MVP-phase working agreement (NexusLink to draft, Blue Virtue to counter-sign) | Vijay to draft | CRITICAL | To draft | Do not authorise developer time until this is signed.
O12 | 2026-08-31 | Infrastructure | VPS access + source-vision.com Cloudflare credentials handover | Blue Virtue | High | Awaiting client | Needed Week 1 of build.
O13 | 2026-08-31 | Commercial | Software sales professional — do they need specific screens / materials / metrics from us? | Blue Virtue | Low | Awaiting client | Nice-to-know for the demo pack.
O14 | 2026-08-31 | Commercial | Who owns demo storyline, product demo script, Acquire listing copy — Blue Virtue confirm? | Blue Virtue | Medium | Awaiting client | Needed before dry run (M6).
O15 | 2026-08-12 | Design ambiguity | Meneer Online iframe instruction sits under 'Customer Dashboard' heading in brief — which screen? | Blue Virtue | Low | Awaiting client | Currently treated as roadmap (see L6).
O16 | 2026-08-31 | Delivery format | How the 'buyer is walked through' — guided recording, live walk-through, or both? | Blue Virtue | Low | Awaiting client | Before dry run.

## IP Register
Component | Origin | Developer | Source / Dependency | Repo / Location | Status | Date added | Notes
Design tokens (CSS variables) | New Source Vision | NexusLink | Blue Virtue design system | source-vision-mvp/assets/css/tokens.css | New development | 2026-09-01 | Colours, radii, spacing scale, type sizes.
Component library (buttons, cards, forms) | New Source Vision | NexusLink | Blue Virtue design system | source-vision-mvp/assets/css/components.css | New development | 2026-09-01 | Buttons, cards, form inputs, stat tiles, badges.
White-label settings screen | New Source Vision | NexusLink | Blue Virtue specification | source-vision-mvp/platform/whitelabel.html | New development | 2026-09-01 | Example row from Blue Virtue's alignment note.
GRS Mailsystem screenshots | GRS (heritage) | GRS (existing) | Provided by Blue Virtue for illustrative use only | source-vision-mvp/assets/images/grs-mail/*.png | REFERENCE ONLY — heritage evidence | 2026-09-01 | Used on Newsletter Overview to prove email heritage. NOT a NexusLink build.
Space Grotesk font | Third-party (OFL) | Google Fonts / OFL | Bundled locally under OFL licence | source-vision-mvp/assets/fonts/ | Third-party (licensed) | 2026-09-01 | OFL licence file included.
Source Vision logo (AI/SVG/PNG) | New Source Vision | Blue Virtue | Blue Virtue creative | source-vision-mvp/assets/images/logo/ | Blue Virtue-provided | 2026-09-01 | Do NOT modify. Only recolour navy/white per usage rules.

## Change Log
Date | Author | Sheet(s) affected | Change summary | Reason
2026-09-01 | Vijay Dabhi | All | Initial workbook created. Pre-populated with 25 locked decisions, 16 open decisions, 6 IP register starter rows. | PM handover pack v1.0.